## Slide 1: Objective for the first year
Dialogue
Ethical, legal and societal aspects/challenges
Cybersecurity

## Slide 2: SPARTA WP2: T2.1 Timeplan
Milestone | Task | Due date
Relevant projects | Identification of relevant projects where partners (MRU, TNK, FHG, Unamur) are involved in - MRU, TNK, FHG, Unamur | 15.07.2019
D2.1 | Workshop questionnaire and issues identification : Preparation of template with first ideas - UNamur Inputs in the template - MRU, TNK, FHG Sending questionnaire to all partners involved in pilots - ? Reception of filled questionnaires from pilots | 15.07.2019 15.08.2019 30.08.2019 20.09.2019
 | Workshop during SPARTA days- All partners | M8
 | Evaluation of each identified issues and challenges and categorization- UNamur | M8
 | Table of content and Identification Partners contribution to the deliverable D2.1 - UNamur | M8-M9
 | Contribution to D2.1 - MRU, TNK, FHG, Unamur | M8-M9-M10-M11
 | Submission for peer review - UNamur | M11
 | Deliverable submission - CEA | M12
Notes: Should we postpone D2.2 and D2.4 to take in consideration the content of deliverables submitted on M12 and M24?