## Slide 1: SPARTA Work Package 2 Responsible innovation: ethical, legal and societal aspects
Michael Friedewald, Daniel Bachlechner, Ralf Lindner (Fraunhofer ISI)

## Slide 2: Who we are
4 core partners
  FHG, DE (WP lead) – 18 PM
  UNamur, BE – 9 PM
  MRU/ Mykolas Romeris Univ., LV – 9 PM
  INOV INESC Inovação, PT – 12 PM
11 further partners – of WP leaders
  CEA, TNK, CETIC, BUT, TUM, IMT, CINI, CNR, L3CE, SMILE, ITTI
  interfaces to the other work packages: provide input to WP 2, communicate WP 2 results to other patners.
  Participate in f2f activities (workshops etc.) in WP 2

## Slide 3: Challenges addressed
Identification of key stakeholders involved in and affected by innovations in cybersecurity
Deriving a consistent set of requirements from a multitude of possibly contradictory needs and concerns
Dealing with limited knowledge of and interest for ethical, legal and societal aspects.
Using an “understandable language” for ethical, legal and societal aspects.

## Slide 4: Ambition
make sure that cybersecurity innovations launched by SPARTA are ethically sound, socially acceptable and compliant with applicable data protection laws
develop effective ELSA structures and processes that be applied also in the context of other transnational competence networks

## Slide 5: Policy and legal background relevant for WP 2
Directive on security of network and information systems (NIS Directive)
  Transposed into national law until May 2018
Cybersecurity package 2017
  EU cybersecurity certification framework
  Revised mandate for ENISA
  Blueprint for rapid emergency response
General Data Protection Regulation GDPR
  applicable directly in all EU member states since 25-05-2018
  almost unified rules for all EU member states
  Art 25 Data Protection by design and by default
  Art 32 Security of processing
ePrivacy Regulation (lex specialis to GDPR for electronic communications)
  still negotiated between the EU institutions
  comprehensive security rules for specific applications

## Slide 6: Goals and objectives
Objective 7: Demonstrate ethical sustainability
  „The consortium will deliver concrete, measurable and actionable results on critical parts of the SPARTA roadmap, through responsible research and innovation, and exploiting Joint Centre of Competence Infrastructures. Where addressing requirements from vertical domains alone would generate ad-hoc solutions that could prove difficult to scale, the combination with innovative horizontal approaches will build leverage and give rise to new and innovative capacities.“
Here: Solutions that are ethically acceptable, legally compliant, socially compatible, i.e.
  are in line with common (public) problem conception and do not raise concerns among citizens
  Proportionate, transparent and ensuring security and confidentiality
  Reconciled (balanced) with other interests, rights and freedoms

## Slide 7: Key concepts
Ethical, legal and social aspects (example from the cybersecurity context)
Key challenges and solution approaches (examples from the cybersecurity context)
ELSA auditing and supervision (explanation of the constructive role)

## Slide 8: State of the art
common features of ELSA efforts and established methods
features (e.g., based on Zwart & Nelis, 2009)
  proximity (closeness to or embedding in large-scale scientific programs)
  early anticipation (of societal issues and potential controversies)
  interactivity (encouraging stakeholders and publics to assume an active role in co-designing research agendas);
  interdisciplinarity (bridging boundaries between research communities)
overview of key methods (e.g., workshops, interviews)
GDPR
Notes: https://www.ncbi.nlm.nih.gov/pmc/articles/PMC2711829/

## Slide 9: Impact expected
Increased awareness of the relevance of ELSA in the cybersecurity context among the members of the SPARTA consortium and beyond
Cybersecurity innovations launched by SPARTA have gone through an ELSA impact assessment
Measures have been taken to avoid serious negative implications resulting from cybersecurity innovations launched by SPARTA

## Slide 10: Activities
Task 2.1 Identification of relevant ethical, legal and societal aspects (M1-12, lead: UNamur)
Task 2.2 Investigation of key challenges and promising solution approaches (M13-24, lead: MRU)
Task 2.3 Formulation of general guidelines for responsible cybersecurity R&I (M7-36, lead: FHG)
Task 2.4 Conversion of approaches into concrete solutions with the SPARTA Programs (M 19-36, lead: FHG)
Task 2.5 Internal ELSA auditing and supervision (M1-36, lead: INOV)

## Slide 11: Inputs, deliverables and outcomes
No. | Deliverable name | Lead partner | Due date
2.1 | Ethical, legal, and societal aspects | UNamur | M12 = Jan 2020
2.2 | First internal ELSA audit and supervision report | INOV | M12 = Jan 2020
2.3 | Key challenges and promising solution approaches | MRU | M24 = Jan 2021
2.4 | Second internal ELSA audit and supervision report | INOV | M24 = Jan 2021
2.5 | Concrete ELSA solutions for the SPARTA programs | FHG | M36 = Jan 2022
2.6 | General guidelines for responsible cybersecurity research and innovation | FHG | M36 = Jan 2022
2.7 | Final internal ELSA audit and supervision report | INOV | M36 = Jan 2022

## Slide 12: Measuring success – KPIs from the DoA
KPI 7.4: # of responsible research and innovation debates and # of participants
  each project year: 1 debate (workshop) with >22 participants
More indicators have to be defined...
  ...based on work going on in important RRI-related policy research for DG CNECT and DG Research (led by Fraunhofer)

## Slide 13: Work organisation principles
ELSA research requires input from stakeholders
  members of the consortium
  external stakeholders
As ethical, legal and societal aspects are closely linked, they are addressed in an integrated form
There is a close relationship between WP2 and WP1
WP2 clearly plays a constructive role (no barrier, no distraction, no conviction)

## Slide 14: Roles and contributions
FHG: coordination of WP activities; focus on ethical and social aspects
UNamur, MRU: focus on (ethical and) legal aspects
TNK: focus on ethical and societal aspects
INOV: ELSA auditing and supervision; focus on gender and diversity aspects
L3CE, IMT, CINI, ITTI: interfaces between ELSA efforts and the SPARTA Programs (WP4-7)
TUM: interface between ELSA efforts and the roadmap efforts (WP3)
CEA: interface to the network governance efforts (WP1)
CNR, BUT, SMILE, CETIC: interfaces to other WPs

## Slide 15: High level plan
Identification of relevant ethical, legal and societal aspects
Investigation of key challenges and solution approaches
Formulation of general guidelines for responsible cybersecurity R&I
Conversion of solution approaches into concrete solutions for the SPARTA Programs
In parallel: Continuous ELSA auditing and supervision

## Slide 16: Interfaces to other WPs
Interfaces between ELSA efforts and the SPARTA Programs (WP4-7): L3CE, IMT, CINI, ITTI
Interface between ELSA efforts and the roadmap efforts (WP3): TUM
Interface to the network governance efforts (WP1): CEA
Interfaces to other WPs:
  Clustering, platforms and ecosystems: CNR
  Training and awareness: BUT
  Exploitation and IPR: SMILE
  Certification: CETIC
  Dissemination and communication: INOV
WP 2 task leaders form the „Ethics Committee“

## Slide 17: Milestones
First year: focus on identification of relevant ethical, legal and societal aspects
Second year: focus on investigation of key challenges and solution approaches
Third year: focus on general guidelines and concrete solutions (efforts start already in the first and second year, respectively)
ELSA audit and supervision reports are provided on a yearly basis (the audits care carried out continuously)
Notes: the official project milestones do not seem to be particularly suitable to be discussed on the WP level

## Slide 18: Next steps
Dedicated WP2 kick-off meeting with core partners
Coordination with interface partners
  Information needs
  Timeline
  Means of communication

## Slide 19: Challenges, issues, questions