**SPARTA**

Task T9.2 Work Plan for 2020

**Task-specific WP9 information:**

Any changes to data in the proposal: No

Main contact for T9.2 WP9: Sara Ricci (ricci@feec.vutbr.cz)

Partners involved in T9.2 WP9: **BUT**, TUM, YWH, CINI, CNIT, PPBW, KTU, UBO, IMT, SMILE, L3CE

Maillist: Rashel Talukder PPBW <rashel.talukder@ppbw.pl>,

Klaudia Kaczmarek <klaudia.kaczmarek@ppbw.pl>,

Nicolas Diaz <n.diaz@yeswehack.com>,

Marc Ohm <ohm@cs.uni-bonn.de>,

Mohammad Norouzian <norouzian@sec.in.tum.de>,

Sara Ricci <ricci@feec.vutbr.cz>,

Jan Hajny <hajny@feec.vutbr.cz>,

Sergej Proskurin <proskurin@sec.in.tum.de>,

Jérôme Jacob <jerome.jacob@securitymadein.lu>, Evaldas Bruze (L3CE) <evaldas@l3ce.eu>,

Nerijus Morkevicius <Nerijus.morkevicius@ktu.edu>,

Olivier Levillain <olivier.levillain@telecom-sudparis.eu>, Giorgio Bernardinetti <giorgio.bernardinetti@cnit.it>, Rocco DE NICOLA <rocco.denicola@imtlucca.it>, Eckert, Claudia <Claudia.Eckert@aisec.fraunhofer.de>

**Plan for 2020 (please list all planned activities):**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|   **ID** | **Quarter**  | **Activity**  | **Output**  | **Partner Responsible** |
| 1  | Q1  | Task Plan Creation | Internal Report (This Document) | BUT |
| 2 | Q1 | Study Program Statistical Analysis | Chapter in D9.2 | BUT |
| 3 | Q1 | Study Map Finalization | Chapter in D9.2 | BUT |
| 4 | Q1 | D9.2 Structure Finalization | D9.2 | BUT |
| 5 | Q1 | Finalization of best practices, chapter in D9.2 delivery | Chapter in D9.2 | CINI |
| 6 | Q1 | Finalization of talent program overview, chapter in D9.2 delivery | Chapter in D9.2 | PPBW |
| 7 | Q1 | Finalization of bug bounty program overview, chapter in D9.2 delivery | Chapter in D9.2 | YWH |
| 8 | Q1 – Q2 | University Curricula Creation | Chapter in D9.2 | BUT |
| 9 | Q1 – Q2 | Professional Curricula Creation | Chapter in D9.2 | IMT |
| 10 | 06/2020 | Delivery D 9.2 ConsolidationStructure: TBD | Chapter in D9.2 | BUT |
| 11 | 7/2020 | D9.2 Review | D9.2 | TUM, UBO, CINI |
| 12 | Q1 | Overview of existing cyber range tools | Chapter in D9.2 | CINI |
| 13 | Q2 – Q4 | Cyber Range Design & Deployment  | Chapter in D9.2 | BUT, CINI |

 **Risk** **Mitigation strategy**

Please Update Please Update

**KPIs:**

 Please Update Please Update

**Dissemination strategy:**

 Please Update